## 갠트 차트 템플릿
Gantt Chart for ML | [6 empty] | Smartsheet 도움말 ➜ | [7 empty] | 갠트 차트의 시각적 타임라인을 사용하면 각 작업의 세부정보는 물론 프로젝트 간의 상호 의존성을 확인할 수 있습니다.
Subject |  | Capstone Design - MS |  |  |  |  | Team name | [8 empty] | Manners Maketh Man
Team member |  | WooSeop Jung, DongHwan Seo, MinJae Baek, DaBin Lee, JungMyung Wi |  |  |  |  | Date | [8 empty] | 2023-04-13
ML Team member |  | MinJae Baek, DaBin Lee, JungMyung Wi
Num | To do | In charge | Begin date | Due date | Period | Progress
[7 empty] | 3.2~ 3.11 | [6 empty] | 3. 12 ~ 3.18 | [6 empty] | 3.19~ 3.31 | [6 empty] | 4.1~ 4. 16 | [6 empty] | 4. 17 ~ 4.23 | [6 empty] | 4.24 ~ 4.30 | [6 empty] | 5.1 ~ 5.7 | [6 empty] | 5.8 ~ 5.14 | [6 empty] | 5.15 ~ 5.21 | [6 empty] | 5.22 ~ 5.28 | [6 empty] | 5.29 ~ 6.4 | [6 empty] | 6.5 ~ 6.11
[7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 | ML model design
1.2 | Model feature analysis | All of ML team members | 2023-04-17 | 2023-04-30 | 14 | 0% | bar: 4. 17 ~ 4.23 Mon to 4.24 ~ 4.30 Sun
1.4 | Text augmentation | All of ML team members | 2023-04-17 | 2023-04-30 | 14 | 0% | bar: 4. 17 ~ 4.23 Mon to 4.24 ~ 4.30 Sun
1.5 | Text embedding | All of ML team members | 2023-04-17 | 2023-04-30 | 14 | 0% | bar: 4. 17 ~ 4.23 Mon to 4.24 ~ 4.30 Sun
1.6 | Trained model | All of ML team members | 2023-05-01 | 2023-05-05 | 5 | 0% | bar: 4.24 ~ 4.30 Mon to 5.1 ~ 5.7 Fri
1.7 | Combine models with ensemble techniques | All of ML team members | 2023-05-06 | 2023-05-08 | 3 | 0% | bar: 5.1 ~ 5.7 Sat to 5.8 ~ 5.14 Mon
1.8 | Optimizing the model | All of ML team members | 2023-05-11 | 2023-05-31 | 21 | 0% | bar: 5.8 ~ 5.14 Thu to 5.29 ~ 6.4 Wed
2 | ML Communication
2.1 | Making proposal | All of ML team members | 2023-04-01 | 2023-04-14 | 14 | 100% | bar: 4.1~ 4. 16 Mon to 4.1~ 4. 16 Wed
2.2 | Determine dataset | All of ML team members | 2023-03-02 | 2023-03-31 | 30 | 100% | bar: 3.2~ 3.11 Mon to 3.19~ 3.31 Sun
2.3 | Model selection | All of ML team members | 2023-03-02 | 2023-03-31 | 30 | 100% | bar: 3.2~ 3.11 Mon to 3.19~ 3.31 Sun
2.4 | Final report | All of ML team members | 2023-05-15 | 2023-06-06 | 23 | 0% | bar: 5.15 ~ 5.21 Mon to 5.29 ~ 6.4 Sun
2.5 | Apply model to program | All of ML team members | 2023-05-15 | 2023-06-06 | 23 | 0% | bar: 5.15 ~ 5.21 Mon to 5.29 ~ 6.4 Sun
Formulas:
Period = SUM(DAYS([Due date],[Begin date]), 1)