## 갠트 차트 템플릿
Gantt Chart for FE & BE | [6 empty] | Smartsheet 도움말 ➜ | [14 empty] | 갠트 차트의 시각적 타임라인을 사용하면 각 작업의 세부정보는 물론 프로젝트 간의 상호 의존성을 확인할 수 있습니다.
Subject |  | Capstone Design - MS |  |  |  |  | Team name | [15 empty] | Manners Maketh Man
Team member |  | WooSeop Jung, DongHwan Seo, MinJae Baek, DaBin Lee, JungMyung Wi |  |  |  |  | Date | [15 empty] | 2023-05-03
Frontend member |  | WooSeop Jung
Backend member |  | DongHwan Seo
Num | To do | In charge | Begin date | Due date | Period | Progress | Stage 1 | [34 empty] | Stage 2 | [23 empty] | Stage 3
[7 empty] | 4.3 ~ 4.9 | [6 empty] | 4.10 ~ 4.16 | [6 empty] | 4.17 ~ 4.23 | [6 empty] | 4.24 ~ 4.30 | [6 empty] | 5.1 ~ 5.7 | [6 empty] | 5.8 ~ 5.14 | [6 empty] | 5.15 ~ 5.21 | [6 empty] | 5.22 ~ 5.28 | [6 empty] | 5.29 ~ 5.31 |  |  | 6.1 ~ 6.4 |  |  |  | 6.5 ~ 6.11
[7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
1 | Constrcucting Basic Structure
1.1 | Crawling conversation by using OCR | WooSeop Jung | 2023-04-03 | 2023-05-07 | 35 | 0% | bar: 4.3 ~ 4.9 Mon to 5.1 ~ 5.7 Sun
1.1.1 | Searching OCR engine |  | 2023-04-03 | 2023-04-23 | 21 | 0% | bar: 4.3 ~ 4.9 Mon to 4.17 ~ 4.23 Sun
1.1.2 | Implmenting OCR engine |  | 2023-04-24 | 2023-05-07 | 14 | 0% | bar: 4.24 ~ 4.30 Mon to 5.1 ~ 5.7 Sun
1.2 | Developing GUI | WooSeop Jung | 2023-04-03 | 2023-04-30 | 28 | 0% | bar: 4.3 ~ 4.9 Mon to 4.24 ~ 4.30 Sun
1.2.1 | Selecting GUI framework |  | 2023-04-03 | 2023-04-06 | 4 | 0% | bar: 4.3 ~ 4.9 Mon to 4.3 ~ 4.9 Thu
1.2.2 | Setting GUI framework |  | 2023-04-07 | 2023-04-11 | 5 | 0% | bar: 4.3 ~ 4.9 Fri to 4.10 ~ 4.16 Tue
1.2.3 | Implementing GUI |  | 2023-04-12 | 2023-04-30 | 19 | 0% | bar: 4.10 ~ 4.16 Wed to 4.24 ~ 4.30 Sun
1.3 | Developing BackEnd | DongHwan Seo | 2023-04-03 | 2023-05-07 | 35 | 0% | bar: 4.3 ~ 4.9 Mon to 5.1 ~ 5.7 Sun
1.3.1 | Selecting BackEnd framework |  | 2023-04-03 | 2023-04-05 | 3 | 0% | bar: 4.3 ~ 4.9 Mon to 4.3 ~ 4.9 Wed
1.3.2 | Setting BackEnd framework |  | 2023-04-06 | 2023-04-10 | 5 | 0% | bar: 4.3 ~ 4.9 Thu to 4.10 ~ 4.16 Mon
1.3.3 | Implementing REST API |  | 2023-04-11 | 2023-04-23 | 13 | 0% | bar: 4.10 ~ 4.16 Tue to 4.17 ~ 4.23 Sun
1.3.4 | Designing DataBase |  | 2023-04-24 | 2023-05-07 | 14 | 0% | bar: 4.24 ~ 4.30 Mon to 5.1 ~ 5.7 Sun
2 | Connecting Components
2.1 | Merging FrontEnd - BackEnd | WooSeop Jung DongHwan Seo | 2023-05-08 | 2023-05-21 | 14 | 0% | bar: 5.8 ~ 5.14 Mon to 5.15 ~ 5.21 Sun
2.2 | Merging BackEnd - Machine Learning | DongHwan Seo | 2023-05-22 | 2023-05-31 | 10 | 0% | bar: 5.22 ~ 5.28 Mon to 5.29 ~ 5.31 Wed
3 | Quality Check
3.1 | Testing | WooSeop Jung DongHwan Seo | 2023-05-31 | 2023-06-04 | 5 | 0% | bar: 6.1 ~ 6.4 Thu to 6.1 ~ 6.4 Sun
3.2 | Debugging | WooSeop Jung DongHwan Seo | 2023-05-31 | 2023-06-04 | 5 | 0% | bar: 6.1 ~ 6.4 Thu to 6.1 ~ 6.4 Sun
3.3 | Deploying | WooSeop Jung DongHwan Seo | 2023-06-05 | 2023-06-11 | 7 | 0% | bar: 6.5 ~ 6.11 Mon to 6.5 ~ 6.11 Sun
Formulas:
Period = SUM(DAYS([Due date],[Begin date]), 1)